## Gantt Chart - Manual Duration
Task Name	Start Date	End Date (expected)	Duration (Days)	Days Complete	Days Remaining	Percent Complete		Start Date in Number Form	15/03/18		Reunion Date	09/04/18
Task One - (privatize game module)	15/03/2018	18/03/2018	3	3,00	0,00	100%
Task Two - (create inventory)	15/03/2018	20/03/2018	5	5,00	0,00	100%
Task Three - (modify player to use inventory)	20/03/2018	24/03/2018	4	4,00	0,00	100%
Task Four - (create link module)	15/03/2018	19/03/2018	4	4,00	0,00	100%
Task Five - (modify space to use links)	19/03/2018	24/03/2018	5	5,00	0,00	100%
Task Six - (game_reader loads links)	24/03/2018	28/03/2018	4	4,00	0,00	100%
Task Seven - (new game visualization to see links)	28/03/2018	01/04/2018	4	4,00	0,00	100%
Task Eight - (modify data files to have links too)	28/03/2018	02/04/2018	5	5,00	0,00	100%
Task Nine - (change displacement to “move north”)	15/03/2018	18/03/2018	3	3,00	0,00	100%
Task Ten - (check command objects)	15/03/2018	20/03/2018	5	5,00	0,00	100%
Task Eleven - (check space command)	20/03/2018	24/03/2018	4	4,00	0,00	100%
Task Twelve - (modify to use the new modules)	24/03/2018	01/04/2018	8	8,00	0,00	100%
Task Thirteen - (modify grasp and drops to use names)	24/03/2018	29/03/2018	5	5,00	0,00	100%
Task Fourteen - (files with commands)	15/03/2018	20/03/2018	5	5,00	0,00	100%
Task Fifteen - (management, meetings and gants)	15/03/2018	09/04/2018	25	25,00	0,00	100%
Task Sixteen - (document using doxygen)	15/03/2018	09/04/2018	25	25,00	0,00	100%
Task Seventeen - (modify Makefile)	02/04/2018	05/04/2018	3	3,00	0,00	100%
Project total (& Debug)	15/03/2018	09/04/2018	25	25,00	0,00	100%

Members	Tasks to be done			TEST FILES
Eric Morales	10, 11, 13, 14			space_test, object_test, player_test
Javier Lougedo	9, 15, 16 (revision), 17			game_test
Victor Yrazustra	4, 5, 6, 8			command_test, link_test
Alejandro Pascual	2, 3, 7			inventory_test, game_reader_test
All	1 (done), 12

## Hoja1
	Javier	Victor	Alejandro	Eric
command
data
die
game_loop
game_reader
game
graphic_engine
object
player
screen
set
space
types
links
inventory
Makefile
Documentation & excel